## Frontend
Project Manager - frontend |  |  | Agent - Frontend |  |  | Admin - Frontend |  |  | Approval - Frontend
1 | create project | Done | 1 | Search coupon | Done | 1 | User Registration | Done | 1 | List of batch for approval | Pending
2 | list of project | Done | 2 | List of sold coupon | Done | 2 | Agent Registration | Done | 2 | Approve batch | Pending
3 | create batch | Done | 3 | Issue Voucher | Done | 3 | Sub Agent Registration | Done | 3 | Batch History | Pending
4 | list of batch | Done |  |  |  | 4 | User list | Done | 4 | List of project for approval | Pending
5 | batch operation | In Progress |  |  |  | 5 | Agent List | Done | 5 | Approve project | Pending
6 | create task | In Progress |  |  |  | 6 | Sub Agent List | Done | 6 | Project Details | Pending
7 | list of task | In Progress
8 | coupon details of voucher | In Progress
9 | project details | In Progress
10 | voucher details of batch | In Progress
11 | Batch History | Done
12 | Search Coupon | Pending
13 | Batch Print Status | In Progress

## Backend
Project Manager - Backend |  |  | Agent - Backend |  |  | Admin - Backend |  |  | Approval - Backend
1 | create project | Done | 1 | Search coupon | Pending | 1 | User Registration | In Prograss | 1 | List of batch for approvsl | Pending
2 | list of project | Done | 2 | List of sold coupon | Pending | 2 | Agent Registration | In Prograss | 2 | Approv batcg | Pending
3 | create batch | In Prograss | 3 | Issue Voucher | Pending | 3 | Sub Agent Registration | In Prograss | 3 | Batch History | Pending
4 | list of batch | Pending |  |  |  | 4 | User list | In Prograss | 4 | List of projet for approval | Pending
5 | batch operation | Pending |  |  |  | 5 | Agent List | In Prograss | 5 | Approv project | Pending
6 | create task | Pending |  |  |  | 6 | Sub Agent List | In Prograss | 6 | Project Deatails | Pending
7 | list of task | Pending
8 | coupon details of voucher | Pending
9 | project details | Pending
10 | voucher details of batch | Pending
11 | Batch History | Pending
12 | Search Coupon | Pending