## 2024.07.19
Project Manager Path - Sasindu | Figma | Created By | Bootstrap | Created By | Database | Created By | BackEnd | Created By | Test | Created By
Login form for project creator | Finish | Geenodh / Hemashi | In Prograss | Sasindu |  |  | In Progass | Ravindu | Completed
List of projects | Finish | Geenodh / Hemashi | Completed | Sasindu |  |  | Completed | Ravindu | In Prograss | Yushuf
Create new project | Finish | Geenodh / Hemashi | Completed | Sasindu |  |  | Completed | Ravindu | Completed | Yushuf
Project details | Finish | Geenodh / Hemashi | Completed | Sasindu |  |  | In Progass | Ravindu | Completed | Tharindi
List of batch | Finish | Geenodh / Hemashi | In Prograss | Sasindu |  |  | Completed | Ravindu | Completed | Tharindi
Create Batch | Finish | Geenodh / Hemashi | In Prograss | Sasindu |  |  | Completed | Ravindu | Completed | Shamodha
Voucher details of a batch | Finish | Geenodh / Hemashi | In Prograss | Sasindu |  |  | ToDo | Ravindu | Completed | Shamodha
Coupon details of a voucher | Finish | Geenodh / Hemashi | In Prograss | Sasindu |  |  | ToDo | Ravindu | Completed | Shamodha
Batch Operation | Finish | Geenodh / Hemashi | In Prograss | Sasindu |  |  | ToDo | Ravindu | Completed | Tharindi
Create print | Finish | Geenodh / Hemashi | Completed | Sasindu |  |  | ToDo | Ravindu | Completed | Tharindi
Batch Operation - add receive date | Finish | Geenodh / Hemashi | In Prograss | Sasindu |  |  | ToDo | Ravindu
Batch history | Finish | Geenodh / Hemashi | Completed | Sasindu |  |  | ToDo | Ravindu | Completed | Tharindi
Search coupon/ voucher | Finish | Geenodh / Hemashi | In Prograss | Sasindu |  |  | ToDo | Ravindu | Completed | Tharindi
List of tasks | Finish | Geenodh / Hemashi | In Prograss | Sasindu |  |  | ToDo | Ravindu
Create/select task | Finish | Geenodh / Hemashi | In Prograss | Sasindu |  |  | ToDo | Ravindu | Completed | Tharindi
Disposal | Finish | Geenodh / Hemashi | In Prograss | Sasindu |  |  | ToDo | Ravindu | Completed | Tharindi
goods received | Finish | Geenodh / Hemashi | In Prograss | Sasindu |  |  | ToDo | Ravindu | Completed | Tharindi
X (Parameters) | Finish | Geenodh / Hemashi | In Prograss | Sasindu |  |  | ToDo | Ravindu | Completed | Asher
Approval Path - Dhananjaya
Login for print aproval | Finish | Geenodh / Hemashi | ToDo |  |  |  | ToDo |  | Completed | Tharindi
List of batch for aproval | Finish | Geenodh / Hemashi | ToDo |  |  |  | ToDo |  | Completed | Tharindi
Aprove batch | Finish | Geenodh / Hemashi | ToDo |  |  |  | ToDo |  | Completed | Tharindi
Batch history | Finish | Geenodh / Hemashi | ToDo |  |  |  | ToDo |  | Completed | Tharindi
List of project for aproval | Finish | Geenodh / Hemashi | ToDo |  |  |  | ToDo
Aprove project | Finish | Geenodh / Hemashi | ToDo |  |  |  | ToDo |  | In Prograss | Yushuf
project details | Finish | Geenodh / Hemashi | ToDo |  |  |  | ToDo
Agent Path - Pabasara
Agent login | Finish | Geenodh / Hemashi | In Prograss |  |  |  | ToDo |  | Completed | Shamodha
List of sold voucher | Finish | Geenodh / Hemashi | In Prograss |  |  |  | ToDo |  | Completed | Shamodha
Search coupon/ voucher sell | Finish | Geenodh / Hemashi | In Prograss |  |  |  | ToDo |  | Completed | Shamodha
Admin Path - Dinusha
Admin login | Finish | Geenodh / Hemashi | ToDo | Dinusha |  |  | ToDo |  | Completed | Yushuf
User list | Finish | Geenodh / Hemashi | Completed | Dinusha |  |  | Completed |  | Completed | Yushuf
User Registration | Finish | Geenodh / Hemashi | Completed | Dinusha |  |  | In Progass |  | Completed | Yushuf
list of projects binded for internal user | Finish | Geenodh / Hemashi | ToDo | Dinusha |  |  | ToDo |  | In Prograss | Yushuf
Bind new project for internal users | Finish | Geenodh / Hemashi | ToDo | Dinusha |  |  | ToDo
List of sub Agent of the external user | Finish | Geenodh / Hemashi | Completed | Dinusha |  |  | Completed |  | Completed | Yushuf
Add Agent (Agent list) | Finish | Geenodh / Hemashi | Completed | Dinusha |  |  | Completed |  | Completed | Yushuf
Add Agent | Finish | Geenodh / Hemashi | Completed | Dinusha |  |  | Completed |  | Completed | Yushuf
Add Sub Agent | Finish | Geenodh / Hemashi | Completed | Dinusha |  |  | Completed |  | Completed | Yushuf

## 2024.07.22
2