## 2024.07.19
Path | Figma | Created By | Bootstrap | Created By | Database | Created By | BackEnd | Created By | Test | Created By
Project Manager Path
Login form for project creator | Completed | Geenodh / Hemashi | In Prograss | Sasindu |  |  | In Prograss | Ravindu | Completed | Yushuf
List of projects | Completed | Geenodh / Hemashi | Completed | Sasindu |  |  | Completed | Ravindu | In Prograss | Yushuf
Create new project | Completed | Geenodh / Hemashi | Completed | Sasindu |  |  | Completed | Ravindu | Completed | Yushuf
Project details | Completed | Geenodh / Hemashi | Completed | Sasindu |  |  | In Prograss | Ravindu | Completed | Tharindi
List of batch | Completed | Geenodh / Hemashi | In Prograss | Sasindu |  |  | Completed | Ravindu | Completed | Tharindi
Create Batch | Completed | Geenodh / Hemashi | In Prograss | Sasindu |  |  | Completed | Ravindu | Completed | Shamodha
Voucher details of a batch | Completed | Geenodh / Hemashi | In Prograss | Sasindu |  |  |  |  | Completed | Shamodha
Coupon details of a voucher | Completed | Geenodh / Hemashi | In Prograss | Sasindu |  |  |  |  | Completed | Shamodha
Batch Operation | Completed | Geenodh / Hemashi | In Prograss | Sasindu |  |  |  |  | Completed | Tharindi
Create print | Completed | Geenodh / Hemashi | Completed | Sasindu |  |  |  |  | Completed | Tharindi
Batch Operation - add receive date | Completed | Geenodh / Hemashi | In Prograss | Sasindu
Batch history | Completed | Geenodh / Hemashi | Completed | Sasindu |  |  |  |  | Completed | Tharindi
Search coupon/ voucher | Completed | Geenodh / Hemashi | In Prograss | Sasindu |  |  |  |  | Completed | Tharindi
List of tasks | Completed | Geenodh / Hemashi | In Prograss | Sasindu
Create/select task | Completed | Geenodh / Hemashi | In Prograss | Sasindu |  |  |  |  | Completed | Tharindi
Disposal | Completed | Geenodh / Hemashi | In Prograss | Sasindu |  |  |  |  | Completed | Tharindi
goods received | Completed | Geenodh / Hemashi | In Prograss | Sasindu |  |  |  |  | Completed | Tharindi
X (Parameters) | Completed | Geenodh / Hemashi | In Prograss | Sasindu |  |  |  |  | Completed | Asher
Approval Path
Login for print aproval | Completed | Geenodh / Hemashi | [6 empty] | Completed | Tharindi
List of batch for aproval | Completed | Geenodh / Hemashi | [6 empty] | Completed | Tharindi
Aprove batch | Completed | Geenodh / Hemashi | [6 empty] | Completed | Tharindi
Batch history | Completed | Geenodh / Hemashi | [6 empty] | Completed | Tharindi
List of project for aproval | Completed | Geenodh / Hemashi
Aprove project | Completed | Geenodh / Hemashi | [6 empty] | In Prograss | Yushuf
project details | Completed | Geenodh / Hemashi
Agent Path
Agent login | Completed | Geenodh / Hemashi | In Prograss | [5 empty] | Completed | Shamodha
List of sold voucher | Completed | Geenodh / Hemashi | In Prograss | [5 empty] | Completed | Shamodha
Search coupon/ voucher sell | Completed | Geenodh / Hemashi | In Prograss | [5 empty] | Completed | Shamodha
Admin Path
Admin login | Completed | Geenodh / Hemashi |  | Dinusha |  |  |  |  | Completed | Yushuf
User list | Completed | Geenodh / Hemashi | Completed | Dinusha |  |  | Completed |  | Completed | Yushuf
User Registration | Completed | Geenodh / Hemashi | Completed | Dinusha |  |  | In Progass |  | Completed | Yushuf
list of projects binded for internal user | Completed | Geenodh / Hemashi | [6 empty] | In Prograss | Yushuf
Bind new project for internal users | Completed | Geenodh / Hemashi
List of sub Agent of the external user | Completed | Geenodh / Hemashi | Completed | Dinusha |  |  | Completed |  | Completed | Yushuf
Add Agent (Agent list) | Completed | Geenodh / Hemashi | Completed | Dinusha |  |  | Completed |  | Completed | Yushuf
Add Agent | Completed | Geenodh / Hemashi | Completed | Dinusha |  |  | Completed |  | Completed | Yushuf
Add Sub Agent | Completed | Geenodh / Hemashi | Completed | Dinusha |  |  | Completed |  | Completed | Yushuf

## 2024.07.22
2