## Form Status
Project Manager |  | Frontend | Backend
1 | create project | Done | Done
2 | list of project | Done | Done
3 | create batch | Done | InProgress
4 | list of batch | Done | Pending
5 | batch operation | In Progress | Pending
6 | create task | In Progress | Pending
7 | list of task | In Progress | Pending
8 | coupon details of voucher | In Progress | Pending
9 | project details | In Progress | Pending
10 | voucher details of batch | In Progress | Pending
11 | Batch History | Done | Pending
12 | Search Coupon | Pending | Pending
13 | Batch Print Status | In Progress | Pending
Agent
1 | Search coupon | Done | Pending
2 | List of sold coupon | Done | Pending
3 | Issue Voucher | Done | Pending
Admin
1 | User Registration | Done | InProgress
2 | Agent Registration | Done | InProgress
3 | Sub Agent Registration | Done | InProgress
4 | User list | Done | InProgress
5 | Agent List | Done | InProgress
6 | Sub Agent List | Done | InProgress
Approval
1 | List of batch for approval | Pending | Pending
2 | Approve batch | Pending | Pending
3 | Batch History | Pending | Pending
4 | List of project for approval | Pending | Pending
5 | Approve project | Pending | Pending
6 | Project Details | Pending | Pending